Solarize [Name of Community]

Dates of Campaign: X/XX/2015 – X/XX/2016

How to use this form: The Community Outreach Planning Form is intended to be a living document that is used at the beginning of the campaign to plan and identify potential outreach opportunities and to be updated throughout the campaign at the team’s bi-weekly meetings. The form will serve as a planning tool, but also help to track the campaigns progress.

Solarize Events (Focus on Residential) (Look at community calendars; workshops at libraries, lunch & learns, upcoming community events, etc. and list campaign events)

| Completed? (X) | Event and Venue (List events) | Date/Time | Result (# of attendees) | Notes | Assign roles |
| --- | --- | --- | --- | --- | --- |
| X | Launch Event; community library | 8/16/15; 7:00pm | 75 | 50 requests for quotes | Nancy – reserve venue; Richard – send out press release; Bill – send email invitation; Betty- print event posters and hand out; Doug – get refreshments |
|  | Apple festival; Smith Orchard | 9/15/15; 2:00pm |  |  | Betty – bring handouts and sign up sheets; Doug – organize volunteers; Nancy – bring chairs and table |

Solarize Events – (Focus on Commercial) (Lunch & Learns at employers, Green Building Associations or business energy events, Technology councils or Chamber of Businesses)

| Completed? (X) | Event and Venue (List events) | Date/Time | Result (# of attendees) | Notes | Assign roles |
| --- | --- | --- | --- | --- | --- |
| X | Lunch & Learn; FedEx office | 8/31/15; 2:00pm | 15 |  | Nancy – print brochures; Bill – confirm with installer |
|  | Chamber of Commerce | 10/15/15 |  |  |  |

Partner Organization Outreach – Who are partner organizations that will spread your message? (Environmental clubs and organizations, faith communities, Boys/Girls Scouts, Rotary Clubs, schools, etc)

| Name | Date | Item | Who/Contact Info | Social Media Addresses |
| --- | --- | --- | --- | --- |
| Sierra Club | Throughout campaign | Email database and social media | Ben Smith; bsmith@google.com | www.facebook.com/sierraclubny |

E-Newsletters – Does your municipality have a newsletter or a partner organization, home owners associations, etc.?

| Name | Date | Item | Who | Completed? |
| --- | --- | --- | --- | --- |

Local Media (Consider print, radio, online publications and social media; who are local reporters (business section, neighborhood/community interest, and, home and garden, and environmental writers)

| Outlet | Date | Story | Who | Completed? |
| --- | --- | --- | --- | --- |

Websites (whose websites will host information about your campaign or events?)

| Name | Date | Item | Who | Completed? |
| --- | --- | --- | --- | --- |
| Solar Installer ABC |  | Webpage | Stan Johnson | X |

Social Media Tracking (when and where were social media posted?)

| Site | Dates | Who/What Posted | Completed? |
| --- | --- | --- | --- |
| Campaign Facebook page | 8/12/15 | Betty/launch event | X |

Flyers/Banners / Mailings (where were flyers posted or mailings sent?)

| What | Where Placed | When | Who is Responsible? |
| --- | --- | --- | --- |

Launch Planning Worksheet

LAUNCH EVENT OUTCOMES:

- Attendees identify lots of neighbors and friends who are also curious about solar.

- Attendees get a good baseline of knowledge about solar and what to expect when going solar.

- Attendees sign up to get a call (and hopefully a site visit!) from your installer.

- Attendees tell others to attend a Solarize workshop, visit the Solarize website, and/or sign up to get a call from your partner installer.

|  | Task | Who is responsible? |
| --- | --- | --- |
|  | Date and time of launch? Date: _______________ Time: ____________ (What day of the week and time works best for your community residents?) |  |
|  | Venue/location :_____________________________ |  |
|  | What style of Launch will you hold?: Workshop OR Meet & Greet |  |
|  | Is there a cost to renting the venue?: _______________ |  |
|  | Will you need projector, screen, microphone, internet access? Does venue supply these? Cost? Are there enough chairs? |  |
|  | Food and/or drinks? Cost? ______________________________ |  |
|  | Will you set up registration? (online, phone, etc). EventBrite is a good, free alternative. |  |
|  | Invite key speakers: - Meeting facilitator/emcee for event - Community leader(s) - Someone respected who would be willing to speak briefly about how great Solarize is. - Solar installers (should wear shirts with logos) - Solar ambassadors/solar owners |  |
|  | Produce event flyers and post in visible areas |  |
|  | Create email invitation to event with links to registration, if using |  |
|  | Send email invitation to partners and email address lists |  |
|  | Create short summary about event to be placed in online calendars and partner newsletters |  |
|  | List event on your website |  |
|  | Set up Facebook event page and invite people to attend |  |
|  | Start regular social media posts |  |
|  | One Week Before |  |
|  | Start more frequent social media posts |  |
|  | Write and send press release to media contacts |  |
|  | Confirm venue and food |  |
|  | Resend email invite |  |
|  | Email registrants and confirm attendance (two days before) |  |
|  | Assign volunteer duties - Registration desk - Refreshments - Audiovisual - Photographer - Clean Up |  |
|  | Create Agenda: (see agenda below) |  |
|  | Prepare presentation, if installer is not providing |  |
|  | Confirm attendance of community leaders who will attend |  |
|  | Do you need laptops/tablets so that attendees can register online for a quote at the event? (does venue have internet access?) |  |
|  | Day of Event |  |
|  | What to Bring: |  |
|  | - Registration List for those who pre-registered and Sign-In list for others |  |
|  | - Name Tags (especially for speakers, team members and installers) |  |
|  | - Pencils/pens |  |
|  | - Campaign flyers or informational handouts, FAQs, etc |  |
|  | - Campaign Banner (take pictures of team and community leader w/ banner) |  |
|  | - Agenda (see sample below) |  |
|  | - Camera |  |
|  | - Directional signs for outside and inside of building, if necessary |  |
|  | - Laptop, speakers, microphone, screen, if needed for presentation |  |
|  | - Misc.: Tape, scissors, string to hang banner, extension cords for AV equipment |  |
|  | - Tablecloths for food tables, cups, napkins, refreshments, if needed |  |
|  | Set up campaign table with campaign flyers, FAQ sheets, financing and energy efficiency information |  |
|  | Set up registration table at entrance of venue (have everyone who did not pre-register sign in |  |
|  | Following the Event |  |
|  | Send thank you to speakers, volunteers and attendees. |  |
|  | Send an email to attendees ad encourage them to sign up for a solar quote |  |

Launch Event AGENDA

Opening (10 min)

- Welcome from event facilitator/emcee – briefly describe Solarize campaign and partners

- Welcome from an enthusiastic municipal leader (if you have one coming)

- Recognize team members and people who already have solar

Solar Installer Presentation (if using just one installer) or “Solar 101 presentation” by team member (20-25 min)

- Solarize volunteer introduces your installer, highlighting why you’re excited to work with them

- Installer introduces themselves and their company (if one Solarize installer). If using multiple installers, just introduce each of them.

- Provide some brief background on solar market in US, in NY, and in your region

- Review the basic solar equipment

- Assume folks in the room may not have any idea what to expect

- Be careful not to get TOO detailed or you’ll lose them all together

- Talk about your tiered pricing, and comment on payback and financing options

- Explain how to get a solar quote. Be sure to give people a good sense of the timeline for getting quote, installation, etc. Encourage them to sign up for a quote before they leave the event.

Q&A (15-20 min)

Stick Around and Mingle – Encourage people to talk with the solar owners, installers and team members and to sign up for a solar quote on one of the computers, if you have them there.