## On_site Energy Mngr
Project Name: | [5 empty] | Reporting Period | Q1 |  | This sheet should be expanded each quarter with new measures. If measure status/savings/cost has updated (i.e. something identified last quarter was installed, M&V refined savings estimates, actual installed cost is known), previous measures should be updated. [version 11_2020]
OsEM Project Number: | [5 empty] | OsEM Start Date:
OsEM Name: | [5 empty] | Electric Energy Savings Target (%): | 3%
OsEM Company: | [5 empty] | Fossil Fuel Energy Savings Target (%): | 5% | [7 empty] | Q1
Q2
On-site Energy Manager Results | [14 empty] | Q3
Energy Type |  | Baseline | Target | Identified (Pipeline) Progress | Installed (Acquired) Progress | % Identified Progress Against Target | % Installed Progress Against Target | % Identified Savings Over Baseline | % Installed Savings Over Baseline | [5 empty] | Q4
Electric (kWh) |  | 5000000 | 250000 | 175000 | 100000 | 70% | 40% | 3.5% | 2% | [5 empty] | Q5
Fossil Fuel (MMBtu) |  | 50000 | 5000 | 750 | 500 | 15% | 10% | 1.5% | 1% |  |  |  |  | Y | Q6
[14 empty] | N | Q7
Details by Project (add rows as needed) | [14 empty] | Q8
ECM# | Measure Description | Measure Location | Quarter Identified/ Installed* | Installed? (Y/N) | Annual Electric Savings, kWh | Summer On-Peak Demand Savings, kW | Fossil Fuel Savings, MMBtu | Fossil Fuel Savings Source** | Cost Savings, $ | Project Cost, $ | Simple Payback Period, years | Incentive Program Pursued | Notes
1 | Measure Name 1 |  | Q1 | Y | 100000 | 4 |  |  | 16000 | 100000 | 6.25
2 | Measure Name 2 |  | Q1 | Y |  |  | 500 | Natural Gas | 10000 | 75000 | 7.5
3 | Measure Name 3 |  | Q1 | N | 75000 | 1 |  |  | 12000 | 50000 | 4.1667
4 | Measure Name 4 |  | Q1 | N |  |  | 250 | Natural Gas | 5000 | 25000 | 5
|  |  |  | TOTAL: | 175000 | 5 | 750 |  | 43000 | 250000 | 5.814
|  |  |  | INSTALLED: | 100000 | 4 | 500 |  | 26000 | 175000 | 6.7308
*This should reflect the most recent milestone for the measure. When a previously identified measure is installed, the quarter should be updated to reflect the installation.
**Fossil fuel savings source = natural gas, compressed natural gas, propane, kerosene, gasoline, diesel fuel, #2 fuel oil, #6 fuel oil, coal, steam, wood, or other. Please indicate source.